## EXAMPLE Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART | [60 empty] | https://goo.gl/ejIdKR
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | 2 | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation | Entire Team | 12 | 11 | 1 |  |  |  |  | 91.67%
1.1 | UI mockup | Entire Team | 2.5 | 2 | 0.5 |  |  |  | 1 | 80% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Architecture design | Entire Team | 1 | 1 | 0 |  |  |  | 1 | 100%
1.2 | UML diagrams | Entire Team | 1.5 | 1.5 | 0 |  |  |  | 1 | 100% | bar: WEEK 2 M to WEEK 3 R
1.3 | Documentation writing | Entire Team | 5 | 4 | 1 |  |  |  | 1 | 80% | bar: WEEK 2 M to WEEK 3 R
1.4 | Effort Estimation | Entire Team | 1 | 1.5 | -0.5 |  |  |  | 1 | 150% | bar: WEEK 2 M to WEEK 3 R
1.5 | Database initialization | Entire Team | 1 | 1 | 0 |  |  |  | 1 | 100% | bar: WEEK 2 M to WEEK 3 R
1.6 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0! | bar: WEEK 3 F
2 |  |  |  |  | 0 |  |  |  |  | #DIV/0!
2.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0! | bar: WEEK 4 M to WEEK 5 F
2.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
2.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
2.4 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3 |  |  |  |  | 0 |  |  |  |  | #DIV/0!
3.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.2.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.2.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.3.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4 |  |  |  |  | 0 |  |  |  |  | #DIV/0!
4.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4.4 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 12 | 11 | 1 | 60 | 0.2 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 12 | 11.8 | 11.6 | 11.4 | 11.2 | 11 | 10.8 | 10.6 | 10.4 | 10.2 | 10 | 9.8 | 9.6 | 9.4 | 9.2 | 9 | 8.8 | 8.6 | 8.4 | 8.2 | 8 | 7.8 | 7.6 | 7.4 | 7.2 | 7 | 6.8 | 6.6 | 6.4 | 6.2 | 6 | 5.8 | 5.6 | 5.4 | 5.2 | 5 | 4.8 | 4.6 | 4.4 | 4.2 | 4 | 3.8 | 3.6 | 3.4 | 3.2 | 3 | 2.8 | 2.6 | 2.4 | 2.2 | 2 | 1.8 | 1.6 | 1.4 | 1.2 | 1 | 0.8 | 0.6 | 0.4 | 0.2
[10 empty] | ESTIMATE | 12 | 4 | -16 | -46 | -86 | -106 | -117 | -133 | -175 | -220 | -240 | -250 | -266 | -290 | -338 | -358 | -362 | -367 | -371 | -379 | -387 | -392 | -397 | -402 | -405 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -20332
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[10 empty] | HRS REMAINING | 4 | -16 | -46 | -86 | -106 | -117 | -133 | -175 | -220 | -240 | -250 | -266 | -290 | -338 | -358 | -362 | -367 | -371 | -379 | -387 | -392 | -397 | -402 | -405 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -407 | -20751
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 07 |  |  |  |  | WEEK 08
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation | Entire Team | 14 | 12.5 | 1.5 | 1 | 2025-09-01 | 2025-09-15 |  | 89.29%
1.1 | UI mockup | Entire Team | 2.5 | 2 | 0.5 | 1 | 2025-09-01 | 2025-09-02 | 2 | 80% | bar: WEEK 1 M to WEEK 1 T; WEEK 3 M to WEEK 3 R; WEEK 5 W
1.1.1 | Architecture design | Entire Team | 1 | 1 | 0 | 1 | 2025-09-03 | 2025-09-03 | 1 | 100% | bar: WEEK 1 W to WEEK 1 R; WEEK 3 M to WEEK 3 R; WEEK 5 W
1.2 | UML diagrams | Entire Team | 1.5 | 1.5 | 0 | 1 | 2025-09-04 | 2025-09-04 | 1 | 100% | bar: WEEK 1 W to WEEK 1 R; WEEK 3 M to WEEK 3 R; WEEK 5 W
1.3 | Documentation writing | Entire Team | 5 | 4 | 1 | 1 | 2025-09-05 | 2025-09-08 | 4 | 80% | bar: WEEK 1 F to WEEK 2 M; WEEK 3 M to WEEK 3 R; WEEK 5 W
1.4 | Effort Estimation | Entire Team | 1 | 1.5 | -0.5 | 1 | 2025-09-11 | 2025-09-11 | 1 | 150% | bar: WEEK 2 W; WEEK 3 M to WEEK 3 R; WEEK 5 W
1.5 | Database initialization | Entire Team | 1 | 1 | 0 | 1 | 2025-09-10 | 2025-09-10 | 1 | 100% | bar: WEEK 2 T; WEEK 3 M to WEEK 3 R; WEEK 5 W
1.6 | Database setup and containerization | Angelo Pio | 2 | 1.5 | 0.5 | 1 | 2025-09-11 | 2025-09-11 | 1 | 75% | bar: WEEK 2 R; WEEK 3 M to WEEK 3 R; WEEK 5 W
2 |  |  | 18 | 17 | 1 | 2 | 2025-09-16 | 2025-09-29 |  | 94.44%
2.1 | Docker set up | Angelo Pio | 1 | 1 | 0 | 2 | 2025-09-16 | 2025-09-16 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W
2.2 | Back end microservice creation, connection to db | Angelo Pio | 3 | 3 | 0 | 2 | 2025-09-17 | 2025-09-18 | 2 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W
2.3 | Auth service microservice creation , connection to db | Alessandro | 3 | 2 | 1 | 2 | 2025-09-19 | 2025-09-19 | 1 | 66.67% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W
2.4 | Back end admin API and models | Angelo Pio | 10 | 10 | 0 | 2 | 2025-09-20 | 2025-09-23 | 4 | 100% | bar: WEEK 3 M to WEEK 4 W; WEEK 5 W
2.5 | Back end - Auth services containerization | Angelo Pio | 1 | 1 | 0 | 2 | 2025-09-16 | 2025-09-16 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W
2.6 | Authentication mechanism | Alessandro | 3 | 3 | 0 | 2 | 2025-09-17 | 2025-09-17 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W
2.7 | Lab manager and Researcher APIs implementation | Angelo Pio | 8 | 8 | 0 | 2 | 2025-09-17 | 2025-09-18 | 2 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W
2.9 | Front End: Login page | Alessandro | 2 | 2 | 0 | 2 | 2025-09-18 | 2025-09-18 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W
2.10 | Front End: Lab Manager Pages | Alessandro | 15 | 16 | -1 | 2 | 2025-09-21 | 2025-09-23 | 3 | 106.7% | bar: WEEK 3 M to WEEK 3 R; WEEK 4 M to WEEK 4 W; WEEK 5 W
3 |  |  | 17 | 14.5 | 2.5 | 3 | 2025-10-30 | 2025-10-13 |  | 85.29%
3.2 | Authentication APIs | Alessandro | 4 | 3 | 1 | 3 | 2025-10-31 | 2025-10-31 | 1 | 75% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 M; WEEK 5 W
3.2.1 | Back End : Report generation | Angelo Pio | 2 | 2 | 0 | 3 | 2025-11-01 | 2025-11-01 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 T to WEEK 5 W
3.3 | Broker microservice creation and containerization | Alessandro | 1 | 1.5 | -0.5 | 3 | 2025-11-02 | 2025-11-02 | 1 | 150% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W
3.3.1 | Front End: Researcher Pages | Alessandro | 10 | 8 | 2 | 3 | 2025-11-02 | 2025-11-03 | 2 | 80% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W to WEEK 5 R
3.3.2 | Notification microservice creation | Angelo Pio | 1 | 1 | 0 | 3 | 2025-11-04 | 2025-11-04 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W; WEEK 5 F
3.3.3 | Notification routine implementation | Angelo Pio | 3 | 2 | 1 | 3 | 2025-11-05 | 2025-11-06 | 2 | 66.67% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W; WEEK 6 M to WEEK 6 T
3.3.4 | Alert mechanism creation | Alessandro | 2 | 2 | 0 | 3 | 2025-11-07 | 2025-11-07 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W; WEEK 6 W
4 |  |  | 42 | 42 | 0 | 4 | 2025-10-14 | 2025-10-25 |  | 100%
4.1 | Report generation improvements | Angelo Pio | 1 | 1 | 0 | 4 | 2025-10-14 | 2025-10-14 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W; WEEK 07 M
4.2 | Back-end bug fixing | Angelo Pio | 5 | 6 | -1 | 4 | 2025-10-15 | 2025-10-16 | 2 | 120% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W; WEEK 07 T to WEEK 07 W
4.3 | Front-End service containerization | Angelo Pio | 1 | 1 | 0 | 4 | 2025-10-17 | 2025-10-17 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W; WEEK 07 F
4.3 | Notification microservice containerization | Angelo Pio | 1 | 1 | 0 | 4 | 2025-10-20 | 2025-10-20 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W; WEEK 08 M
4.3 | Front End: Admin Pages | Alessandro | 8 | 8 | 0 | 4 | 2025-10-21 | 2025-10-23 | 3 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W; WEEK 08 T to WEEK 08 R
4.3 | Front end: Dashboard graph creation | Aessandro | 4 | 4 | 0 | 4 | 2025-10-24 | 2025-10-24 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W; WEEK 08 F
4.3 | System testing and UI improvements | Entire Team | 10 | 9 | 1 | 4 | 2025-10-21 | 2025-10-23 | 3 | 90% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W; WEEK 08 M to WEEK 08 W
4.4 | Bug fixing | Entire Team | 12 | 12 | 0 | 4 | 2025-10-23 | 2025-10-25 | 3 | 100% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 W; WEEK 08 W to WEEK 08 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS | [43 empty] | TOTAL HOURS
| BURNDOWN DATA | TOTAL HOURS | 91 | 86 | 5 | 60 | 1.5167 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 91 | 89.4833 | 87.9667 | 86.45 | 84.9333 | 83.4167 | 81.9 | 80.3833 | 78.8667 | 77.35 | 75.8333 | 74.3167 | 72.8 | 71.2833 | 69.7667 | 68.25 | 66.7333 | 65.2167 | 63.7 | 62.1833 | 60.6667 | 59.15 | 57.6333 | 56.1167 | 54.6 | 53.0833 | 51.5667 | 50.05 | 48.5333 | 47.0167 | 45.5 | 43.9833 | 42.4667 | 40.95 | 39.4333 | 37.9167 | 36.4 | 34.8833 | 33.3667 | 31.85 | 2457
[10 empty] | ESTIMATE | 91 | 89 | 88 | 86.5 | 82.5 | 81 | 80 | 78.5 | 77.5 | 74.5 | 72.5 | 62.5 | 61.5 | 58.5 | 50.5 | 48.5 | 32.5 | 29.5 | 27.5 | 26 | 18 | 17 | 15 | 13 | 12 | 6 | 5 | 4 | -4 | -8 | -17 | -29 | -29 | -29 | -29 | -29 | -29 | -29 | -29 | -29 | 1098
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 2 | 1 | 1.5 | 4 | 1.5 | 1 | 1.5 | 1 | 3 | 2 | 10 | 1 | 3 | 8 | 2 | 16 | 3 | 2 | 1.5 | 8 | 1 | 2 | 2 | 1 | 6 | 1 | 1 | 8 | 4 | 9 | 12
[10 empty] | HRS REMAINING | 89 | 88 | 86.5 | 82.5 | 81 | 80 | 78.5 | 77.5 | 74.5 | 72.5 | 62.5 | 61.5 | 58.5 | 50.5 | 48.5 | 32.5 | 29.5 | 27.5 | 26 | 18 | 17 | 15 | 13 | 12 | 6 | 5 | 4 | -4 | -8 | -17 | -29 | -29 | -29 | -29 | -29 | -29 | -29 | -29 | -29 | -29 | 978
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
[6 empty] | 1 | Not Started |  | Not Started | 1
[6 empty] | 2 | In Progress |  | In Progress | 2
[6 empty] | 8 | Completed |  | Completed | 4
[6 empty] | 8 | Not Started |  |  | 8
[6 empty] | 4 |  |  |  | 16
[6 empty] | 80 |  |  |  | 24
[6 empty] | 16 |  |  |  | 40
[6 empty] | 8 |  |  |  | 80
4
2
24
40
8

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED